## Summary
Integration Joint Board - Strategic Risk Register IJBAC January 2024
Risk Code | Risk Owner | Strategic Risk Event | Previous | Current | Target
Risk Rating
IJBSR1 | Chief Officer, Health and Social Care | Failure to plan for strategic change | 16 | 12 | 6
IJBSR2 | Chief Officer, Health and Social Care | Workforce. Inability to attract and retain workforce to deliver delegated services | 16 | 20 | 9
IJBSR3 | Chief Officer, Health and Social Care | Increasing demand for delegated services. Demand outstrips capacity | 12 | 12 | 6
IJBSR4 | Chief Finance Officer, IJB | Insufficient financial resources in order for the partnership to deliver is statutory obligations | 20 | 25 | 12
IJBSR5 | Chief Officer, Health and Social Care | Organisational, professional and cultural barriers inhibit the ability of the H&SCP and in turn the Board to develop services and deliver on strategic ambition | 12 | 12 | 6
Risk amalgamation
The previous risks have been reviewed and captured in the new risk register. The risk summary is
derived as follows:
SR1 replaces SR 1, 3 and 6
SR2 replaces SR 8
SR3 replaces SR 4
SR4 replaces SR 5 and 9
SR5 replaces Sr 2, 7 and 10
SR11 was predicated on global pandemic. SG are focusing on recovery planning as evidenced in
Annual Delivery Plans and PHS no longer supporting Test and Protect

## Risk Register
Western Isles IJB Strategic Risk Register
Risk ID | TITLE | Date Raised | Area/ Department | Exec Lead | Descriptor | Controls (assurance) | Gaps in Controls | Further Mitigation Actions | Initial Score | Aim | Current Score | Previous Score | Target Score | Target Date to Achieve Aim | Review Date(s) | Movement indicator
IJB SR1 | Failure to plan for strategic change | 2022-12-08 | Board Wide | Chief Officer | The cumulative impact of the lack of capacity, expertise and operational system challenges prevent the Chief Officer and senior officers from planning for strategic change to meet the health and social care needs of the population of the Western Isles | A draft Strategic Framework was publisedin June 2023. The framework is designed to guide the production of annual delivery plans for the parent organisations. Furthermore the Directions issued to the parent bodies set out clear guidance for the financial year. In year directions are informed by the Strategic Framework. In addition the Health & Social Care Partnership Senior Leadershipteam has been re-established and will have oversight of service design and change in order to plan for the health and social care needs of the Western Isles | Operational oversight and competeing service pressures lead to capacity challenges within the senior leadership team of the Health and Social Care Partnership. Alongside this is the lack of analytical support re epidemiology / Population Health Needs Assessment. | In addition the Health & Social Care Partnership Senior Leadershipteam has been re-established and will have oversight of service design and change in order to plan for the health and social care needs of the Western Isles. This sits alongside quarterly review of the performace indicators for the IJB. | High - 16 | Reduce risk | Moderate - 12 | High - 16 | Low - 6 | 31.03.24 | 28.02.24
IJB SR2 | Worforce. Inability to attract and retain workforce to deliver delegated services | 2022-12-08 | Board Wide | Chief Officer | The workforce risk is multifaced. Specifically the skill shortage of individuals qualifying across a number of disciplines, depopulation and reducing population of working age in Western Isles a significant driver for the risk. | Active tracking of current vacancy through HR systems, senior officers & monthly financial monitoring identifying gaps within individual service lines. In addition quarterly finanace/workforce reporting through Audit and onwards to IJB | Anticipated impact of poulation decline predicated on ONS and GP parctice lists sizes. To date no significant impact or oversight from CPP to arrest the poulation decline through supported inward migration aligned to economic prsperity and development of housing stock to support poulation growth. | Proactive recruitment planning in partnership with HR in 2 parent bodies. Parent bodies have well developed workforce plans and strategy. CnES and NHS WI have well developed workforce strategies. CO & DoF (NHS) acive engagement with cross-cutting themes with Scottish Governement Directorates. Sharing of best practice through H&SCScotland | High -16 | Tolerate/manage | High - 20 | High - 16 | Moderate - 6 | 31.03.26 | 28.02.24
IJB SR3 | Increasing demand for delegated services. Demand outstrips capacity | 2022-12-08 | Board Wide | Chief Officer | Increasing demand for delegated services. Demand outstrips capacity as a irect impact of the changing Western Isles demographics. Data (local and national) indicates increasing bursen of disease (forecast incresae of 21% by 2043) and health and social care challenges associates with multimorbidity. Western Isles ageing population leading to greater multi morbidity. | Monthly monitoring of performance metrics through MSG indicators and wider national returns to both Scottish Government and Public Health Scotland. In addition monitoring of waiting lists/service access data alongside complaints management and learning reviews | Restricted ability to refocus resources due to current service demand and wider recruitment challenges into prevenative serevices with the anticiapted system benefits of reducing demand (medium term). Local comprehensive SNA requires updating. | Developemnt of options re models of care including most importantly third sector and community assets to ensure the H&SCP is well placed to meet need of individuals. Look to strong international evidence base to inform development of both parctice and system design | Moderate - 12 | Reduce risk | Moderate - 12 | Moderate - 12 | Low - 6 | 31.03.25 | 28.02.24
IJB SR4 | Insufficient financial resources in order for the partnership to deliver is statutory obligations | 2022-12-08 | Board Wide | Chief Finance Officer | Reducing envelope of total funding received through NHSWI and CnES as a dircet result of funding decisions in very challenged financial construct nationally. In additionthe forecast position regarding reserves further compounds the financial risk. The current risk is futher compounded by high level locum spend in specific service lines. | Rigorous financial planning and monthly budget monitoring which includes financial effeciency savings. In addition consideration to strategic commissioning to realise financial effeciency alongside robust HR processes focusing on sickness and absence that gives rise to agency spend. | Current recruitmeny parctices whilst operating with good governnace arrangeents lack significant innovation regarding reach and marketing Western Isles as preferred career/life destination to redice high level agency spend. | The correspondance with SG (in particular with NHS Scotland and in turn COSLA) indicates a significant reduction.in funding for 24-25 and beyond. Notwithstanding the workforce challenges (outline below) the IJB will be required to scrutinise all investment decison whilst endeavouring to protcet frontline service delivery. Development of wider national recruitment strategy to be supported by innovative approaches to reduce both agency spend alongside the ability to innovate regarding models of care/service delivery alongside the existing workforce. | High - 20 | Reduce risk | High - 25 | High - 20 | Moderate - 12 | 31.03.25 | 28.02.24
IJB SR5 | Organisational, professional and cultural barriers inhibit the ability of the H&SCP and in turn the IJB to develop services and deliver on strategic ambition | 2022-12-08 | Board Wide | Chief Officer | Different organisational views emerge about system development iinfluenced by/and/or esponding to changes in national policy e.g NCS/Verity House Agreement. The cultural differencesl and governance arrangements within CnES and NHS WI may impede progress interms of wider sytem working and innovation. The known national differenes in employment terms and conditions may see worforce eroded in one of the main partner organisations. Professional relationships and competing intersts impacting the IJB ability to discharge its legal responsibilities. | Foster strong corporate working and jjoint executive leadership between CO and resapective CEOs. Stregthen the governace arrangements for CnEs and NHS WI e.g ICMT. Maintain high visibilty of H&SCP senior leadership team to promote/role model partnership working | Mechanisms to fully explore developing proposals/alternatives to current partnership arrangements against a changing national backdrop | Strengthern the active particiaptiion and engagement in new and emergent thinking within the Integration Joint Board. This requires active particiaption odf all Board members consistently through the annual business cycle of meetings/engagement | Moderate - 12 | Reduce risk | Moderate - 12 | Moderate - 12 | Low - 6 | 31.03.25 | 28.02.24
[12 empty] | AIM | Remove
Reduce
Tolerate/Manage

## Risk Appetite Statement
Western Isles Joint Integration Board
Risk Appetite Statement 2023
Health & Social Care systems are one of the most complex organisations. Risk is ever present across and throughout our systems, services and care delivery. Many strategic and operational decisions are underpinned by risk assessment, identifying action, management and reduction. It is important for the Integration Joint Board to be explicit about its approach to, and tolerance of risk, i.e. its Risk Appetite.
The Integration Joint Board, as a strategic ethical commissioning body for Health and Social Care services, seeks to operate within a low overall risk range. As an organisation we place the safety of those using our services as our highest priority, and will not accept known, unmanaged risks that materially impact negatively on those using or providing services.
Our lowest risk appetite relates to patients, clients and staff safety, and compliance requirements. This means that colleagues across the Health and Social Care Partnership are expected to pro-actively consider current available evidence and take action(s) to reduce to reasonably practicable levels, identified risks that originate from or are present within current or planned care and treatment systems, options, equipment, and environment.
We have a marginally higher risk appetite towards delivery of the boards corporate responsibilities, including strategies, finance and population health improvement, the impact(s) of which may be longer term.
Our highest risk appetite as a strategic board relates to the pursuit of innovation in new models of integrated care delivery and the introduction of digital technology including AI (artificial Intelligence), where significant positive gains in terms of positive experience and outcomes are established, or can be anticipated, within the constraints of the regulatory environment and authorised limits.
The IJB and all colleagues within the Health and Social Care Partnership are required to work within our established risk management, reporting and escalation systems, and are expected at all levels, to proactively identify, assess , manage, mitigate, remove or escalate risk on an ongoing basis.
During major incidents that place the service(s) locally and or nationally on an emergency footing the Integration Joint Board accepts the fluid, escalating and rapidly changing nature of such events, decisions will be taken and recorded in the face of presenting situation, available information, resource availability and real time risk-based prioritisation.
Chief Officer
Integration Joint Board
September 2023

## Risk Management Matrix
When considering the scoring matrix good practice indicates that the likelihood and severity scores should be supported with a richer descriptor which helps inform the risk rating. Therefore it is recommended that the following descriptors will help inform the total risk score:
Likelihood | Rare | Unlikely | Possible | Likely | Almost Certain
Probability | 0-15% | 16-35% | 36-60% | 61-80% | 81-100%
Chance of occurrence | Hard to imagine | Unlikely to happen | Reasonable chance of occurring | More likely to occur than not | Hard to imagine not happening
Timeframe | Greater than 5 years | Between 3-4 years | Likely between 2-3 years | Likely between 1-2 years | Likely within 6-12 months
Impact | Negligible | Minor | Moderate | Major | Catastrophic
Effect on outcomes | Minimal Impact | Minor short term effect | Part failure to achieve outcomes | Significant failure to achieve outcomes | Unable to meet delegated service delivery
Reputational damage | None | Minor | Moderate loss of confidence locally | Major loss of confidence nationally/ adverse publicity | Severe loss of confidence. Significant damaging/ adverse public outcry
Regulatory Impact | Verbal guidance/ advice | Formal recommendation from regulator(s) | Improvement notice/ Findings Audit Scotland | Failure in duty of care/ | Corporate